## Roadmap
0
Now / Next / Later • Updated March 2026 • iOS Native SwiftUI • Zero Dependencies
# | Initiative | Description | Priority | Effort
▶ NOW — Active / This Month (High Confidence)
1 | Content Expansion | Add 4 new modules: Electrical Safety, Fire Protection, Ergonomics, Respiratory Protection. 10 questions each → 180 total questions. | P0 | Medium
2 | Adaptive Difficulty Tuning | Calibrate AdaptiveDifficultyManager thresholds based on user feedback. Ensure difficulty ramp feels fair across all 14 existing modules. | P0 | Small
3 | App Store Optimization | Update screenshots for iPhone 16/iPad, refine keywords, add App Preview video. Push v1.1 build. | P0 | Small
4 | Bug Fixes & Polish | Address feedback tab reports: fix edge cases in streak reset logic, quiz timer display on smaller screens, VoiceOver label gaps. | P0 | Small
5 | Onboarding Flow Refinement | Polish OnboardingPathView and RoleSelectionView based on early user data. Reduce steps, clarify role picker. | P1 | Small
⏭ NEXT — 1–3 Months (Planned, Scoped)
1 | Spaced Repetition Engine | Implement algorithm for quiz review scheduling. Surface missed questions at optimal intervals to maximize long-term retention. | P1 | Medium
2 | Leaderboard (Local/Unit) | Optional anonymous leaderboard within a unit code. No account required — unit code entered locally, data stays on device via shared UserDefaults suite or iCloud key-value. | P1 | Medium
4 | Scenario Branching Expansion | Add multi-path decision trees to existing scenarios. Each scenario gets 2-3 branching paths with different outcomes and feedback. | P2 | Medium
6 | Study Plan / Guided Paths | Let users pick a training track (e.g., 'New Inspector 30-Day Plan', 'Annual Refresher') that sequences modules and sets daily goals automatically. | P2 | Medium
⏩ LATER — 3–6+ Months (Directional, Strategic)
1 | Base-Specific Content Packs | Configurable content layers for specific installations. Units can load supplemental procedures on top of the standard 1S0 curriculum. | P2 | Large
2 | AI-Powered Question Generation | On-device ML model or API-assisted generation of new quiz questions from uploaded AFIs/TOs. Keeps content fresh without manual authoring. | P3 | Large
3 | Multi-AFSC Expansion | Extend platform beyond 1S0 to adjacent safety AFSCs (e.g., 4B0 Bioenvironmental, 4E0 Public Health). Same engine, different content packs. | P3 | Large

## Dependencies
DEPENDENCY MAP
Initiative | Depends On | Type | Mitigation | Status
Offline Content Updates | Static hosting (GitHub Pages) | External | Already have docs/ hosted on GitHub Pages — extend for JSON manifests | Ready
Leaderboard (Local/Unit) | iCloud key-value or shared defaults | Technical | Use UserDefaults app group first; iCloud KVS as upgrade path | Needs Scoping
Base-Specific Content Packs | Offline Content Updates | Sequential | Must ship content update system first; packs are just additional JSON bundles | Blocked
Multi-AFSC Expansion | Base-Specific Content Packs | Sequential | Reuse content pack architecture; new AFSC = new content bundle | Blocked
Instructor Dashboard | Leaderboard / unit code system | Sequential | Build on unit identification from leaderboard feature | Blocked
AI Question Generation | Content validation pipeline | Knowledge | Need SME review workflow before auto-generated questions go live | Needs Research
Apple Watch Companion | None (standalone target) | Technical | Shares QuizBank and TrainingModels via shared framework target | Ready
Spaced Repetition Engine | ProgressStore refactor | Technical | Add per-question tracking to ProgressStore (currently module-level only) | Needs Scoping
Scenario Branching | TrainingContent data model update | Technical | Extend Scenario struct with branch nodes; backward compatible | Ready